## Overview
Sprint 2 Planning Overview
Workstreams | 4
Tasks in detailed breakdown | 10
Sprint focus | Carry over uncompleted Sprint 1 work before expanding intelligence features.

## Sprint 2 Plan
Sprint 2 ¦ Planned Increment
Carry over uncompleted Sprint 1 work before expanding intelligence features.
Task ID | Task / Workstream | Planned Work | Priority | Owner | Status | Notes
01 | Advisor Profile Work | Close outstanding auth, advisor UI and integration work | High |  | Not Started
02 | Degree progress | Compute requirement-group and credit completion | High |  | Not Started
03 | Academic risk | Prepare training dataset, baseline model and thresholds | High |  | Not Started
04 | AI foundations | SHAP explanations and approved knowledge ingestion | High |  | Not Started

## Task Breakdown
Task ID | Workstream | Subtask | Acceptance Criteria / Deliverable | Owner | Estimate (hrs) | Status | Dependencies
01 | Advisor Profile Work | Complete authentication work | Required authentication flow works and is tested | PRANALI |  | Not Started
01 | Advisor Profile Work | Finish advisor UI | Advisor profile screens are complete and reviewed | PRANALI |  | Not Started
01 | Advisor Profile Work | Complete integrations | Required advisor integrations work end-to-end | PRANALI |  | Not Started
W
02 | Degree progress | Implement requirement-group calculations | Requirement groups show correct completion status |  |  | Not Started
02 | Degree progress | Implement credit completion calculations | Earned and required credits are calculated correctly |  |  | Not Started
03 | Academic risk | Prepare training dataset | Dataset is cleaned, documented, and ready for training |  |  | Not Started
03 | Academic risk | Build baseline model | Baseline model trains and produces risk predictions |  |  | Not Started
03 | Academic risk | Set risk thresholds | Thresholds are documented and linked to model outputs |  |  | Not Started
04 | AI foundations | Add SHAP explanations | Model predictions have interpretable SHAP explanations |  |  | Not Started
04 | AI foundations | Ingest approved knowledge | Approved sources are ingested and retrievable |  |  | Not Started