## Tasks
Key | Summary | Assignee | Priority | Sprint | Start | Due | Story Points | Status | Completed Date
SCRUM-16 | [UI/UX] Wireframes for Acadmate | Lyno Takudzwa Chihwehwete | High | Sprint-1 | 2026-09-21 | 2026-09-25 | 5 | Done | 2026-09-23
SCRUM-17 | [Backend] Authentication & Roles | Pranali Dukhande | Highest | Sprint-1 | 2026-09-21 | 2026-09-29 | 9 | Done | 2026-09-30
SCRUM-18 | [Database] Academic Data | Datta Vardhan Reddy Kontham | Highest | Sprint-1 | 2026-09-21 | 2026-09-30 | 10 | Done | 2026-09-28
SCRUM-19 | [Backend] Backend APIs | Liangxian Li | Highest | Sprint-2 | 2026-09-28 | 2026-10-06 | 8 | Done | 2026-10-05
SCRUM-20 | [Frontend] Student Dashboard | Lyno Takudzwa Chihwehwete | High | Sprint-2 | 2026-10-01 | 2026-10-09 | 9 | Done | 2026-10-09
SCRUM-21 | [Frontend] Advisor Dashboard | Lyno Takudzwa Chihwehwete | High | Sprint-2 | 2026-10-01 | 2026-10-09 | 9 | Done | 2026-10-09
SCRUM-22 | [Full-stack] Frontend-Backend Integration | Pranali Dukhande | High | Sprint-3 | 2026-10-07 | 2026-10-14 | 7 | Done | 2026-10-15
SCRUM-23 | [QA] Basic Testing | Pragnan Chintu | Medium | Sprint-3 | 2026-10-12 | 2026-10-19 | 7 | Done | 2026-10-19

## Burndown
Date | Day | Ideal Remaining | Actual Remaining | Total Story Points (all tasks) | 110
2026-09-21 | Mon | 110 | 110
2026-09-22 | Tue | 106.1 | 110
2026-09-23 | Wed | 102.1 | 105
2026-09-24 | Thu | 98.2 | 105
2026-09-25 | Fri | 94.3 | 105
2026-09-26 | Sat | 90.4 | 85
2026-09-27 | Sun | 86.4 | 85
2026-09-28 | Mon | 82.5 | 85
2026-09-29 | Tue | 78.6 | 85
2026-09-30 | Wed | 74.6 | 78
2026-10-01 | Thu | 70.7 | 78
2026-10-02 | Fri | 66.8 | 78
2026-10-03 | Sat | 62.9 | 60
2026-10-04 | Sun | 58.9 | 60
2026-10-05 | Mon | 55 | 60
2026-10-06 | Tue | 51.1 | 60
2026-10-07 | Wed | 47.1 | 43
2026-10-08 | Thu | 43.2 | 43
2026-10-09 | Fri | 39.3 | 39
2026-10-10 | Sat | 35.4 | 39
2026-10-11 | Sun | 31.4 | 39
2026-10-12 | Mon | 27.5 | 32
2026-10-13 | Tue | 23.6 | 30
2026-10-14 | Wed | 19.6 | 28
2026-10-15 | Thu | 15.7 | 25
2026-10-16 | Fri | 11.8 | 19
2026-10-17 | Sat | 7.9 | 10
2026-10-18 | Sun | 3.9 | 6
2026-10-19 | Mon | 0 | 0

## README
Sprint 2 Burndown - How to use
1. On the Tasks sheet, fill in Story Points (col H, yellow) for each task.
4. Burndown covers the full project, Sep 21 - Oct 19; ideal line assumes even progress across all 64 points.
3. The Burndown sheet and chart update automatically from those columns.
4. Ideal line assumes even progress Oct 1 - Oct 9; actual line burns points on each task's Completed Date.
5. Attach this file to the Jira sprint, or screenshot the chart into the presentation.